

ELECTORAL COMMISSION OF GHANA

PROGRAMME OF ACTIVITIES FOR 2023

DISTRICT LEVEL ELECTIONS

|  |  |  |  |
| --- | --- | --- | --- |
| **REGISTRATION OF VOTERS** | | | |
| **S/N** | **PERIOD** | **NO. OF DAYS** | **ACTIVITY** |
| 1 | 10/01-10/03/2023 | 60 | Procurement of Educational, Registration, Exhibition and Election Materials |
| 2 | 10/01-10/03/2023 | 60 | Distribution of Registration Materials |
| 3 | 10/01/2023 | 1 | IPAC Meeting on Continuous Registration |
| 4 | 10/01/2023 | 1 | Press release on Continuous Registration |
| 5 | 10/01-30/01/2023 | 14 | Preparation and Distribution of BVR Kits |
| 6 | 12/01-13/01/2023 | 2 | RIPAC & DIPAC |
| 7 | 24/01-30/01/2023 | 7 | Testing of the VMS in the Districts |
| 8 | 31/01/2023 | 1 | IPAC Meeting on Continuous Registration |
| 9 | 31/01/2023 | 1 | Press release on Continuous Registration |
| 10 | 02/02-03/02/2023 | 2 | RIPAC & DIPAC on Continuous Registration |
| 11 | 06/02-07/02/2023 | 2 | KTT |
| 12 | 09/02-10/02/2023 | 2 | T.O.T |
| 13 | 09/02-06/03/2023 | 26 | Publicity on Continuous Registration |
| 14 | 09/02-06/03/2023 | 26 | Media Engagement on Continuous Registration |
| 15 | 12/02-14/02/2023 | 3 | Briefing of District Staff(Technical & Procedure) |
| 16 | **16/02/2023** |  | **Continuous Registration of Voters** |
| 17 | 30/04/2023 | 1 | Briefing & Swearing in of DRRC members |
| 18 | 01/04-14/04/2023 | 14 | Sitting of DRRC, challenges & adjudications |
| 19 | 14/04-28/04/2023 | 15 | Deduplication and adjudication |
| **EXHIBITION OF THE VOTERS REGISTER** | | | |
| 20 | 11/04-30/04/2023 | 20 | Distribution of Exhibition materials |
| 21 | 17/04-23/04/2023 | 7 | Recruitment of Exhibition Supervisors and Officials |
| 22 | 24/04-26/04/2023 | 3 | Keying in of Exhibition Officials data |
| 23 | 25/04-26/04/2023 | 2 | KTT |
| 24 | 28/04/2023 | 1 | Data freeze |
| 25 | 28/04-02/05/2023 | 5 | Data processing and Splitting of Polling Stations |
| 26 | 28/04-02/05/2023 | 5 | Printing and Distribution of Training Registers |
| 27 | 28/04-25/05/2023 | 28 | Printing & Distribution of Provisional Registers |
| 28 | 02/05/2023 | 1 | IPAC Meeting |
| 29 | 02/05/2023 | 1 | Press release on Exhibition of the Voters register |
| 30 | 04/05-05/05/2023 | 2 | RIPAC and DIPAC |
| 31 | 08/05-09/05/2023 | 2 | T.O.T. on Exhibition Procedures |
| 32 | 12/05-19/05/2023 | 8 | Grassroots training for Exhibition Officials |
| 33 | 15/05-26/05/2023 | 12 | Publicity on exhibition and posting of Educational Posters |
| 34 | 15/05-29/05/2023 | 15 | Media Engagement |
| 35 | **02/06-10/06/2023** | **8** | **Exhibition of the Voters Register** |
| 36 | 07/06/2023 | 1 | Appointment and briefing of Revising Officers |
| 37 | 08/06-22/06/2023 | 15 | Adjudication, Keying in of corrections and inclusions |
| 38 | 19/06-23/06/2023 | 5 | Authentication of Voters Register |
| **DISTRICT LEVEL ELECTIONS** | | | |
| 39 | 09/06-14/06/2023 | 5 | Stakeholder Engagements (Women, CSOs, PWDs) – National, Regional & District levels |
| 40 | 12/06-17/06/2023 | 6 | Distribution & Posting of Notices, Nomination Forms, Transfer and Proxy forms |
| 41 | 12/06-16/06/2023 | 5 | Interview & appointment of Returning officers and Deputy Returning Officers |
| 42 | 20/06/2023 | 1 | Press Release on Elections, Nomination of Candidates ,Recruitment of Election Officials, transfers and proxies |
| 43 | 26/06/2023 | 1 | Issuance of Writ |
| 44 | 26/06/2023 | 1 | Gazette publication of Writ of Election |
| 45 | 17/05-21/05/2023 | 5 | Transfer of Votes for Candidates |
| 46 | 26/06/2023 | 1 | Press release on Nomination of Candidates |
| 47 | 29/06/2023 | 1 | Briefing on Receipt of Nomination |
| 48 | **03/07/-07/07/2023** | **2** | **Receipt of Nomination-District Assembly Election** |
| 49 | **03/07/-07/07/2023** | **2** | **Receipt of Nomination-Unit Committee Election** |
| 50 | 10/07-14/07/2023 | 5 | Processing and submission of Nomination forms to Head Office |
| 51 | 13/07-17/07/2023 | 5 | Posting of Notice of Nominations |
| 52 | 13/07-10/09/2023 | 60 | Distribution of other election materials |
| 53 | 16/07-19/09/2023 | 60 | Processing, Printing and Distribution of Notice of Poll and Ballot Papers. |
| 54 | 03/08/2023 | 1 | Press release on IPAC Meeting |
| 55 | 04/08-02/10/2023 | 60 | Publicity on DLE |
| 56 | 08/08-17/08/2023 | 10 | Recruitment and keying in details of election officials in the VMS |
| 57 | **10/08/-21/08/2023** | **11** | **Transfer of Votes / Proxies** |
| 58 | 14/08-18/08/2023 | 5 | Dialogue with Candidates at District Levels |
| 59 | 19/08-28/08/2023 | 10 | Printing and Distribution of Training Registers. |
| 60 | 18/08-22/08/2023 | 5 | KTT for Top Trainers |
| 61 | 23/08-24/08/2023 | 2 | KTT |
| 62 | 23/08/2023 | 1 | Final Data Freeze |
| 63 | 29/08-08/09/2023 | 11 | TOT - Procedure & Technical |
| 64 | 23/08-21/09/2023 | 30 | Data Processing, Splitting of Polling Stations, Generation of Barcodes & Extraction of Data for BVD |
| 65 | 29/08-27/09/2023 | 30 | Preparation and Distribution of BVDs for Training and Election |
| 66 | 31/08-20/09/2023 | 21 | Printing and Distribution of Final Voters Register |
| 67 | 01/09-30/09/2023 | 30 | Media Engagement |
| 68 | 10/09-15/09/2023 | 6 | Posting of Notice of Poll |
| 69 | 12/09-30/09/2023 | 19 | Grassroots training – Procedure & Technical |
| 70 | 12/09-16/09/2023 | 5 | Servicing of Public Address System |
| 71 | 13/09/2023 | 1 | Press Release on the Platform Mounting |
| 72 | 14/09/2023 | 1 | Briefing of Platform Monitors |
| 73 | 17/09-30/09/2023 | 14 | Platform Mounting |
| 74 | 19/09/2023 | 1 | National Meeting to assess Final Preparation on Elections |
| 75 | 21/09/2023 | 1 | Press Release on Elections |
| 76 | **03/10/2023** | **1** | **Election Day** |
| 77 | 04/10-08/10/1023 | 5 | Submission of DLE Results to the Regions & Head Office |
| 78 | 9/10-11/10/2023 | 3 | Submission of Writ of Election to the District Assembly |
| 79 | 18/10/2023 | 1 | Breaking of Ties for DLE |
| 80 | 25/10-26/10/2023 | 2 | Gazette Publication of DLE Results |

NB.

Some of the dates will be subject to change depending on the exigencies of the time.